## Status Summary
Assessing Status on Vermont EPMO Projects
| Green | Yellow | Red
Scope | No outstanding changes that have not been formally approved and logged. | Additions/deletions being acted on without formal sponsor approval. | Out of scope and unfunded work being done, remaining work ignored, previous warning not being acted on.
Schedule | Tasks are starting and ending on time and 90% are on track to meet dates. | 75%+ of tasks are starting and ending on time and 90% are on track to meet dates. | Less than 75% of tasks are starting and ending on time and are on track to meet dates.
Budget | Costs for tasks and phases are less than 110% of baseline costs for same. | Costs for tasks and phases are less than 125% of baseline costs for same. | Costs for tasks and phases are greater than 125% of baseline costs for same.
Resources | Resources are available and engaged according to the timeline. | Resources are constrained due to competing priorities resulting in minor scheduling delays. | Resources are not available creating a project stoppage.
Quality | Quality Expectations are being met according to deliverable expectation documents. | 85% of deliverables are meeting quality expectations. | Less than 85% of deliverables are meeting quality expectations resulting in defects and issus with release management.
Overall | All status categories are on track. | Status categories are experiencing delays or changes but the risks/issues are being mitigated. | Significant issues lead the team to believe the proejct is in jeopardy, the team is unable to remove blockers and leadership intervention is needed to resolve issues.